## Sheet1
PRODUCT BACKLOG |  | Team: Superficial Solutions | Date: | 2017-03-26
Priority | Hours Estimate | Item | Item Type | Done (yes/no)
1 | 4 | Business Requirements | Notes/Analysis | Yes
2 | 4 | Business Rules | Notes/Analysis | Yes
3 | 45 | Vision and Scope Document | Document | Yes
4 | 10 | User Requirements | Notes/Analysis | Yes
5 | 12 | Quality Attributes | Notes/Analysis | Yes
6 | 30 | User Requirements Document | Document | Yes
7 | 10 | Functional UI Prototype | Notes/Analysis | No
8 | 8 | External Interfaces | Notes/Analysis | No
9 | 6 | Constraints analysis | Notes/Analysis | No
10 | 8 | System Requirements | Notes/Analysis | No
11 | 8 | Functional Requirements | Notes/Analysis | No
12 | 30 | Software Requirements Specification Document | Document | No
Done: Designed/implemented, tested, integrated (go-live usable)
Total Hours: | 175